## Cover
🚀 Salesforce Production Deployment Checklist
Complete each tab in sequence — record status, owner, and date for every item
DEPLOYMENT DETAILS
Project / Release Name
Deployment Date
Deploy Window (UTC)
Release Manager
Tech Lead
SF Org ID (Production)
API / Release Version
CHECKLIST TABS
| 1. Governance | CAB approval, stakeholder sign-off, communications, documentation
| 2. Branching & Deploy | Branch strategy, PR process, package composition, environment promotion
| 3. Pre-Deployment | Code review, Apex testing, Salesforce config, portal & integration checks
| 4. Deployment Day | Pre-window checks, execution, post-deploy config, monitoring
| 5. Post-Deployment | Sign-off, comms, documentation, sandbox hygiene, retrospective
| 6. Smoke Tests (Prod) | Production test cases: access, records, flows, files, portal, integrations

## 1. Governance
Salesforce Production Deployment — Governance & Change Management
# | Task / Check | Owner | Priority | Status | Notes | Done By | Date
📋 CHANGE MANAGEMENT
1 | Change Advisory Board (CAB) ticket raised with full impact assessment | Release Mgr | Critical | ☐ Pending
2 | CAB approval obtained (signature / ticket status = Approved) | Release Mgr | Critical | ☐ Pending
3 | Deployment window confirmed and blocked in team calendar | Release Mgr | Critical | ☐ Pending
4 | Maintenance / freeze window exclusions checked (month-end, peak trading) | Release Mgr | Critical | ☐ Pending
5 | Emergency change procedure invoked if outside standard window | Release Mgr | High | ☐ Pending
📣 STAKEHOLDER SIGN-OFF
1 | Business stakeholder UAT sign-off obtained (written / ticket) | Business | Critical | ☐ Pending
2 | Tech lead sign-off on deployment package completeness | Tech Lead | Critical | ☐ Pending
3 | Security / compliance review completed (if data model or access changes) | Security | High | ☐ Pending
4 | Legal / privacy review completed (if PII fields or retention changes) | Legal | High | ☐ Pending
📣 COMMUNICATIONS
1 | Affected users / business units notified of deployment window | Release Mgr | High | ☐ Pending
2 | Support / helpdesk team briefed on changes and known impacts | Release Mgr | High | ☐ Pending
3 | Rollback decision authority identified and available during window | Release Mgr | Critical | ☐ Pending
4 | Escalation contact list distributed to deployment team | Release Mgr | High | ☐ Pending
5 | Post-deploy comms drafted and ready to send on go-live confirmation | Release Mgr | Medium | ☐ Pending
📝 DOCUMENTATION
1 | Deployment runbook / step-by-step script finalised | Dev Lead | Critical | ☐ Pending
2 | Rollback plan documented and tested in sandbox | Dev Lead | Critical | ☐ Pending
3 | Release notes covering all changes, dependencies, and known issues | Dev Lead | High | ☐ Pending
4 | Updated data dictionary / ERD if schema changed | Dev Lead | Medium | ☐ Pending
5 | Architecture / sequence diagrams updated (Flows, integrations) | Dev Lead | Medium | ☐ Pending
STATUS: ☐ Pending ¦ ✅ Done ¦ ⚠ Blocked ¦ N/A ¦ Skipped
Critical | Must complete — deploy blocked if missed
High | Should complete — risk if skipped
Medium | Best practice — low risk if deferred

## 2. Branching & Deploy
Salesforce Production Deployment — Branching & Deployment Strategy
# | Task / Check | Owner | Priority | Status | Notes | Done By | Date
🌿 BRANCH STRATEGY
1 | Feature branches named consistently: feature/<ticket-id>-description | Developer | High | ☐ Pending
2 | All feature branches branched off develop (not main/master) | Developer | Critical | ☐ Pending
3 | No direct commits to main / master / release branch | Dev Lead | Critical | ☐ Pending
4 | Long-lived feature branches rebased / merged with develop before PR | Developer | High | ☐ Pending
5 | Hotfix branches created from main and merged back to both main + develop | Dev Lead | High | ☐ Pending
🔀 PULL REQUEST & MERGE
1 | All PRs peer-reviewed by at least one other developer before merge | Dev Lead | Critical | ☐ Pending
2 | PR linked to Jira / Azure DevOps ticket | Developer | High | ☐ Pending
3 | All CI checks (linting, PMD, unit tests) pass before merge | Developer | Critical | ☐ Pending
4 | Squash merge or standard merge policy followed consistently | Dev Lead | Medium | ☐ Pending
5 | develop branch merged into release branch for this release cycle | Dev Lead | Critical | ☐ Pending
📦 PACKAGE / CHANGESET COMPOSITION
1 | Deployment method confirmed: Salesforce CLI (sf deploy) / Change Set / Unlocked Package | Dev Lead | Critical | ☐ Pending
2 | package.xml / manifest reviewed — all components explicitly listed | Dev Lead | Critical | ☐ Pending
3 | No sandbox-specific components (mock classes, test data loaders) included | Developer | Critical | ☐ Pending
4 | Destructive changes in a separate package (destructiveChanges.xml) and reviewed | Dev Lead | Critical | ☐ Pending
5 | API version on all metadata consistent with target org API version | Developer | High | ☐ Pending
6 | Unlocked package version bumped and dependencies resolved (if applicable) | Dev Lead | High | ☐ Pending
🏗️ ENVIRONMENT PROMOTION PATH
1 | Code promoted through: Dev Sandbox → Full Sandbox → Production (no skipping) | Dev Lead | Critical | ☐ Pending
2 | Full sandbox used for final UAT and validation deploy — not partial or developer sandbox | Dev Lead | Critical | ☐ Pending
3 | Validate-only (check-only) deploy run against production — all tests pass | Dev Lead | Critical | ☐ Pending
4 | Validation deploy result screenshot / log saved for audit trail | Dev Lead | High | ☐ Pending
5 | Quick deploy used only if validation completed within last 10 days | Dev Lead | High | ☐ Pending
6 | CI/CD pipeline run log attached to CAB ticket (if automated pipeline used) | Dev Lead | Medium | ☐ Pending
🏷️ VERSION CONTROL HYGIENE
1 | Release tag created in Git: v<major>.<minor>.<patch> aligned to release notes | Dev Lead | High | ☐ Pending
2 | main branch reflects exact production state after successful deploy | Dev Lead | Critical | ☐ Pending
3 | develop branch reset / synced with main post-deployment | Dev Lead | High | ☐ Pending
4 | Stale feature branches deleted after merge | Developer | Medium | ☐ Pending
STATUS: ☐ Pending ¦ ✅ Done ¦ ⚠ Blocked ¦ N/A ¦ Skipped
Critical | Must complete — deploy blocked if missed
High | Should complete — risk if skipped
Medium | Best practice — low risk if deferred

## 3. Pre-Deployment
Salesforce Production Deployment — Pre-Deployment Checks
# | Task / Check | Owner | Priority | Status | Notes | Done By | Date
🔍 CODE & METADATA REVIEW
1 | No hardcoded Org IDs, Record Type IDs, User IDs, or sandbox URLs | Developer | Critical | ☐ Pending
2 | System.debug statements removed or wrapped in a debug flag | Developer | High | ☐ Pending
3 | SOQL / DML inside loops eliminated — bulk-safe code verified | Developer | Critical | ☐ Pending
4 | Governor limit analysis done for largest expected data volumes | Developer | Critical | ☐ Pending
5 | Custom metadata / custom setting values verified for production values | Developer | High | ☐ Pending
6 | Named credentials and remote site settings documented and ready | Developer | High | ☐ Pending
7 | Profile and permission set changes reviewed — no unintended access removal | Dev Lead | Critical | ☐ Pending
8 | Field-level security (FLS) verified for all new / changed fields | Dev Lead | High | ☐ Pending
9 | Sharing rules and OWD changes impact-assessed | Dev Lead | High | ☐ Pending
🧪 APEX TESTING
1 | All Apex unit tests pass in full sandbox | Developer | Critical | ☐ Pending
2 | Org-wide Apex code coverage ≥ 75% in full sandbox | Developer | Critical | ☐ Pending
3 | Each new / changed class individually ≥ 75% (target ≥ 90%) | Developer | Critical | ☐ Pending
4 | Test classes use @TestSetup and avoid SeeAllData=true | Developer | High | ☐ Pending
5 | Bulk test scenarios included (200-record lists) for triggers and batch | Developer | High | ☐ Pending
6 | Negative / exception path tests included | Developer | High | ☐ Pending
⚙️ SALESFORCE CONFIGURATION CHECKS
1 | All new / changed Flows set to correct API version and active status confirmed | Admin | Critical | ☐ Pending
2 | Flow interview fault paths tested (fault connector present on all elements) | Admin | High | ☐ Pending
3 | Screen Flow visibility confirmed for target profiles / permission sets | Admin | Critical | ☐ Pending
4 | Email templates and letterheads reviewed for production org branding | Admin | High | ☐ Pending
5 | Workflow rules / Process Builders being replaced confirmed as Inactive in prod | Admin | High | ☐ Pending
6 | Validation rules reviewed — no sandbox-only bypass logic | Admin | High | ☐ Pending
7 | Reports and dashboards folder sharing confirmed for target user groups | Admin | Medium | ☐ Pending
8 | List views sharing / visibility set correctly | Admin | Medium | ☐ Pending
🌐 EXPERIENCE CLOUD (PORTAL)
1 | Experience Builder pages published to correct audience (profile / permission set) | Admin | High | ☐ Pending
2 | Guest user profile: no unintended object / field access added | Admin | Critical | ☐ Pending
3 | Authenticated user profile: new object/field access granted where required | Admin | Critical | ☐ Pending
4 | ContentDocumentLink sharing verified: portal users can access generated files | Developer | High | ☐ Pending
5 | Content Distribution / public link expiry settings reviewed | Developer | Medium | ☐ Pending
🔗 INTEGRATIONS & AUTOMATION
1 | Connected app OAuth scopes reviewed — no scope creep | Dev Lead | High | ☐ Pending
2 | Scheduled Apex / batch job schedules confirmed for production timezone | Developer | High | ☐ Pending
3 | Platform Events / Change Data Capture consumers notified of schema changes | Dev Lead | High | ☐ Pending
4 | External system owners notified of API endpoint or payload changes | Dev Lead | High | ☐ Pending
STATUS: ☐ Pending ¦ ✅ Done ¦ ⚠ Blocked ¦ N/A ¦ Skipped
Critical | Must complete — deploy blocked if missed
High | Should complete — risk if skipped
Medium | Best practice — low risk if deferred

## 4. Deployment Day
Salesforce Production Deployment — Deployment Day Execution
# | Task / Check | Owner | Priority | Status | Notes | Done By | Date
🔒 PRE-WINDOW
1 | Production org login confirmed — no MFA or SSO issues for deployer | Dev Lead | Critical | ☐ Pending
2 | No conflicting active deployments or locked metadata in production | Dev Lead | Critical | ☐ Pending
3 | Pre-deploy Apex test coverage snapshot recorded | Dev Lead | High | ☐ Pending
4 | Scheduled Apex jobs paused if they touch affected objects / classes | Dev Lead | High | ☐ Pending
5 | Active integration polling / middleware paused if schema is changing | Dev Lead | High | ☐ Pending
6 | Maintenance banner enabled on Experience Cloud sites (if applicable) | Admin | Medium | ☐ Pending
🚀 EXECUTION
1 | Deploy metadata package to production (sf deploy / Change Set / Package) | Dev Lead | Critical | ☐ Pending
2 | Monitor deployment progress in real-time — no errors or test failures | Dev Lead | Critical | ☐ Pending
3 | All Apex tests ran and passed in production deploy output | Dev Lead | Critical | ☐ Pending
4 | Production Apex coverage ≥ 75% confirmed in deploy results | Dev Lead | Critical | ☐ Pending
5 | Destructive changes package deployed separately (if applicable) | Dev Lead | Critical | ☐ Pending
6 | Quick deploy completed within 10-day validation window (if using quick deploy) | Dev Lead | High | ☐ Pending
⚙️ POST-DEPLOY CONFIGURATION
1 | Flows activated / deactivated per release notes | Admin | Critical | ☐ Pending
2 | Custom metadata records updated in production (if not in package) | Admin | High | ☐ Pending
3 | Custom settings updated in production (if not in package) | Admin | High | ☐ Pending
4 | Experience Cloud site cache cleared and site republished | Admin | High | ☐ Pending
5 | Scheduled Apex jobs re-scheduled with correct times | Dev Lead | High | ☐ Pending
6 | Integrations / middleware re-enabled and connection tested | Dev Lead | High | ☐ Pending
7 | Email deliverability confirmed (if org-wide email address changed) | Admin | Medium | ☐ Pending
8 | Maintenance banner removed from Experience Cloud sites | Admin | High | ☐ Pending
📊 MONITORING
1 | Setup → Apex Jobs — no failures in first 15 minutes | Dev Lead | Critical | ☐ Pending
2 | Setup → Event Log / Debug Logs — no unexpected errors | Dev Lead | High | ☐ Pending
3 | Platform Events / CDC consumers processing events normally | Dev Lead | High | ☐ Pending
4 | Support channels monitored for user-reported issues (first 2 hours) | Release Mgr | High | ☐ Pending
STATUS: ☐ Pending ¦ ✅ Done ¦ ⚠ Blocked ¦ N/A ¦ Skipped
Critical | Must complete — deploy blocked if missed
High | Should complete — risk if skipped
Medium | Best practice — low risk if deferred

## 5. Post-Deployment
Salesforce Production Deployment — Post-Deployment & Sign-Off
# | Task / Check | Owner | Priority | Status | Notes | Done By | Date
✅ SIGN-OFF
1 | Smoke test results reviewed — all Critical tests passed | Tech Lead | Critical | ☐ Pending
2 | Tech lead confirms no rollback required | Tech Lead | Critical | ☐ Pending
3 | Business stakeholder go-live confirmation obtained | Business | Critical | ☐ Pending
4 | CAB / change ticket updated: outcome = Successful, closed | Release Mgr | Critical | ☐ Pending
📣 COMMUNICATIONS
1 | Go-live confirmation email / Slack sent to stakeholders | Release Mgr | High | ☐ Pending
2 | Support / helpdesk notified: system live, known issues documented | Release Mgr | High | ☐ Pending
3 | Affected users notified of new features / changes | Release Mgr | Medium | ☐ Pending
📝 DOCUMENTATION
1 | Release notes published to internal wiki / Confluence | Dev Lead | High | ☐ Pending
2 | Deployment log (components, versions, test results) archived | Dev Lead | High | ☐ Pending
3 | Git release tag verified: main = production state | Dev Lead | High | ☐ Pending
4 | Architecture diagrams updated if structure changed | Dev Lead | Medium | ☐ Pending
🔄 SANDBOX HYGIENE
1 | Full sandbox refresh from production scheduled | Admin | High | ☐ Pending
2 | Developer sandboxes updated with production config changes | Admin | Medium | ☐ Pending
3 | Connected app / OAuth credentials refreshed in sandboxes post-refresh | Dev Lead | Medium | ☐ Pending
📈 RETROSPECTIVE
1 | Deployment retrospective scheduled within 5 business days | Release Mgr | Medium | ☐ Pending
2 | Lessons learned documented and added to team runbook | Team | Medium | ☐ Pending
3 | Checklist updated with new items discovered this deployment | Dev Lead | Medium | ☐ Pending
STATUS: ☐ Pending ¦ ✅ Done ¦ ⚠ Blocked ¦ N/A ¦ Skipped
Critical | Must complete — deploy blocked if missed
High | Should complete — risk if skipped
Medium | Best practice — low risk if deferred

## 6. Smoke Tests (Prod)
Salesforce Production Deployment — Post-Deploy Smoke Tests
Run these test cases in PRODUCTION immediately after deployment. All Critical items must pass before go-live confirmation.
# | Area | Test Case | Expected Result | Priority | Result | Actual / Notes | Tested By | Date
🔐 LOGIN & ACCESS
1 | Login | Standard user can log in to production without errors | Login completes, no error page or MFA loop | Critical | ☐
2 | Login | Portal / community user can log in to Experience Cloud site | Portal home page loads for authenticated user | Critical | ☐
3 | Login | System admin can access Setup without permission errors | Setup menu accessible, no access error | High | ☐
4 | Profiles | New permission set / profile changes applied to test user — no access lost | User can access all previously accessible records | Critical | ☐
📋 CORE SALESFORCE FUNCTIONALITY
1 | Records | Create a new record on each changed object | Record saves successfully, no validation errors | Critical | ☐
2 | Records | Edit an existing record on each changed object | Record updates successfully | Critical | ☐
3 | Records | Delete a record on a changed object (if delete allowed) | Record deleted without error | High | ☐
4 | Fields | All new custom fields visible and editable for correct profiles | Fields appear on page layout, save correctly | High | ☐
5 | Fields | FLS: fields hidden from profiles that should not see them | Hidden fields not visible on record page | High | ☐
6 | Lookups | Lookup / relationship fields resolve correctly | Related record name populates, no broken reference | High | ☐
7 | Lists | Key list views load with correct data | List view displays expected records and columns | Medium | ☐
⚡ FLOWS & AUTOMATION
1 | Screen Flow | Trigger target Screen Flow from its launch point (button / tab) | Flow opens, navigates through all screens without error | Critical | ☐
2 | Screen Flow | Complete Screen Flow end-to-end — verify output record / file created | Output record saved correctly, confirmation shown | Critical | ☐
3 | Auto Flow | Trigger record-triggered Flow (create or update the record) | Flow executes, downstream records/fields updated as expected | Critical | ☐
4 | Scheduled | Scheduled Flow / batch runs at expected time (verify Apex Jobs) | Job shows Completed status, no failures in Apex Jobs | High | ☐
5 | Apex Trigger | Create / update record that fires an Apex trigger — no unhandled exceptions | Record saved, trigger logic applied, no debug errors | Critical | ☐
6 | Batch Apex | Manually invoke batch job — verify it completes for a sample data set | Batch status = Completed, records processed as expected | High | ☐
📄 FILE GENERATION & CONTENT
1 | CSV Export | Run the data export flow — verify CSV file is generated | ContentVersion record created with correct file name | Critical | ☐
2 | CSV Export | Download the generated CSV file as the triggering user | File downloads successfully, data is correct | Critical | ☐
3 | Portal File | Portal user can view and download their generated file | File accessible from portal, no INSUFFICIENT_ACCESS error | Critical | ☐
4 | Permissions | Other users cannot access files they do not own | File not visible/accessible to unrelated users | High | ☐
5 | ContentDist | Public / expiring content distribution link works (if used) | Link opens file, expires at configured time | Medium | ☐
🌐 EXPERIENCE CLOUD (PORTAL)
1 | Pages | All published Experience Cloud pages load without errors | Pages load, no Aura / LWC error banners | Critical | ☐
2 | Pages | Navigation menu items all resolve correctly | Each nav item routes to correct page | High | ☐
3 | Screen Flow | Portal Screen Flow visible and launchable by authenticated user | Flow component renders on portal page | Critical | ☐
4 | Screen Flow | Portal Screen Flow completes end-to-end as community user | Flow completes, output confirmed, no permission errors | Critical | ☐
5 | Guest | Guest user cannot access pages / data requiring authentication | Redirected to login page when accessing restricted content | High | ☐
6 | Search | Global / object search returns results for portal user | Search returns relevant records user has access to | Medium | ☐
📧 EMAIL & NOTIFICATIONS
1 | Email | Trigger an automated email (workflow / flow) — verify delivery | Email received by recipient, merge fields populated correctly | High | ☐
2 | Template | Email template renders correctly with correct branding / logo | No broken images, correct sender name / address | High | ☐
3 | Alerts | In-app notification or chatter post fires as expected | Notification appears for correct user | Medium | ☐
🔗 INTEGRATIONS
1 | Outbound | Trigger an outbound API call / webhook — verify it reaches external system | External system receives correct payload, returns 200 | Critical | ☐
2 | Inbound | Send a test payload to Salesforce inbound endpoint — verify record created/updated | Record created/updated in Salesforce as expected | Critical | ☐
3 | Named Cred | Connected app / named credential used in Apex callout — no auth error | Callout succeeds, no INVALID_SESSION_ID or 401 errors | High | ☐
4 | Platform Ev | Publish a Platform Event — verify subscriber receives and processes it | Subscriber trigger fires, result record updated | High | ☐
📊 REPORTS & DASHBOARDS
1 | Reports | Key reports run and return data without errors | Report loads, row count > 0, no timeout | Medium | ☐
2 | Dashboards | Key dashboards refresh and display correct components | All dashboard components render, no 'insufficient access' | Medium | ☐
RESULT OPTIONS: ☐ Not Tested ¦ ✅ Pass ¦ ❌ Fail ¦ ⚠ Partial ¦ N/A
✅ Pass | Behaviour matches expected result exactly
❌ Fail | Raise P1 incident — block go-live confirmation
⚠ Partial | Partial pass — document deviation and assess risk